## Slide 1
Denotes reforms to be completed in FY 2017-18
INSTRUCTIONS FOR REFORMS IMPLEMENTATION (2015-18)
KINDLY UPLOAD ALL THE DOCUMENTS SUPPORTING REFORM COMPLETION EVIDENCE TO YOUR ULB WEBSITE
HYPERLINK YOUR ANNEXURES TO THE ANNEXURE COLUMN AGAINST EACH REFORMS MILESTONE SUPPORTING YOUR MILESTONE STATUS.
MILESTONING SHOWING “STATE INITIATIVE” IN STATUS COLUMN IS THE REFORM AT STATE LEVEL , HOWEVER IF THERE IS ANY INITIATIVE DONE BY ULB AGAINST IT . KINDLY MENTION IT.
NAGAR PALIKA PARISHAD JAUNPUR

## Slide 2
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
1 - E Governance |  |  |  | 
1 | Creation of Website | Sept 2016 | Completed http://www.nppjaunpuronline.org | ANNEX 1.1
2 | Publication of e-newsletter, Digital India Support | Sept 2016 | Prepared & uploaded e-newsletters of march 2018 on NPP website | ANNEX 1.2
3 | Support Digital India (ducting to be done on PPP mode or by the ULB itself.) | Sept 2016 | As of now there is no such initiative taken to support of digital india.However, as per GO UP GO No286/nau-9-2014-161Ja/12. dated 11-04-2014. Contract with Reliance Jio is in the process for laying ofc in jaunpur city area. | ANNEX 1.3.1 & ANNEX 1.3.2
4 | Coverage with E-MAAS (from the date of hosting the software) Registration of Birth, Death and Marriage, Water & Sewerage Charges, Grievance Redressal, Property Tax, Advertisement tax, Issuance of Licenses, Building Permissions, Mutations, Payroll, Pension and e- procurement | March 2017 | Only registration of death and birth in executed online on web site csrorgi.gov.in. BIRTH and DEATH registration start on enagar sewa soon And grievance redressel is executed nagar palika website www.nppjaunpuronline.org Already it will covert on enagar sewa website and Online property tax , water & sewerage ,issuance of Licenses & mutation is going on website e-nagarsewaup.gov.in | ANNEX 1.4.1 ANNEX 1.4.2 ANNEX 1.4.3 ANNEX 1.4.4 ANNEX 1.4.5 ANNEX 1.4.6 ANNEX 1.4.7 ANNEX 1.4.8 ANNEX 1.4.9 ANNEX 1.4.10 ANNEX 1.4.11
Uttar Pradesh- Reform Milestones under AMRUT

## Slide 3
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
1 - E Governance (contd..) |  |  |  | 
5 | Personnel Staff Management 1.Personal information data of staff 2.Online notification of Recrutment Rules for all municipal cadres 3.Online Up-to-date service records/staff details and seniority lists of last two years;2015-16 and 2016-17 4.Online Bio-metric attendance system 5.Online payment of salaries& wages 6.Online employees grievance redressal system 7.Sou-motu disclosure under RTI act on website | Mar 2018 | Personal information data of non centralize staff uploaded on npp website under process snapshot is attached Online notification of Recruitment Rules for all municipal cadres evidence is uploaded on npp website offline seniority lists is under process for uploaded online up-to-date service records. Offline Bio-metric attendance system in NPP jaunpur & under procress for online Not implemented yet . Not implemented yet . Implemented but not uploaded on web. | ANNEX 1.5.1 ANNEX 1.5.2 ANNEX 1.5.3 ANNEX 1.5.4 ANNEX 1.5.5 ANNEX 1.5.6 ANNEX 1.5.7
6 | Project Management A. Online project management information system Financial & physical progress B. E-tendering for project Online issue of notice inviting tender(NIT) And providing tender documents online Online submission of tender including online paymeny ofEMD C. Online payment to consultant/contactor/vendeors D Geo-tagging of assets created | Mar 2018 | Jaunpur water supply house connection has been done by up jalnigam jaunpur theire physical progress 2506 nos. connection & financial progress 16% complected till now updated on pms snapshot atteched Online issue of NIT snapshot is atteched Online payments to consultant/ contractor/ vendors is not started . Geo-tagging of assets created is not started yet . | ANNEX 1.6.A ANNEX 1.6.B ANNEX 1.6.C ANNEX 1.6.D
2 - Constitution and Professionalization of municipal cadre |  |  |  | 
1 | Policy for engagement of interns in ULBs and implementation | Sept 2016 | Policy for engagement of interns in ULBs has been issued as per Govt. Order No.:2034/ukS-5-16-38lk/2016dated 06-07-2016. | ANNEX 2.1
2 | Establishment of municipal cadre | March 2017 | The list of centralized and Non- centralized employees is enclosed as ANNEX 2.2 | ANNEX 2.2
3 | Cadre linked training | March 2017 | RUCES has conducted the training for capacity building program. Various officials from jaunpur npp have participated in the program. The list of employees who were participated in the training is enclosed as ANNEX 2.3 | ANNEX 2.3
4 | The State will prepare a Policy for Right-sizing the number of municipal functionaries depending on, say, population of the ULB, generation of internal resources and expenditure on salaries. | March 2018 | STATE INITIATIVE | ANNEX 2.4
Uttar Pradesh- Reform Milestones under AMRUT

## Slide 4
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
3 - Augmenting Double Entry Accounting |  |  |  | 
1 | Complete migration to double entry accounting system and obtaining an audit certificate to the effect from FY 2012-13 onwards. | Sept 2016 | Audited Balance sheets of below FY: 2012-13 2013-14 2014-15 2015-16 2016-17 | ANNEX 3.1 (ANNEX 3.1.1,ANNEX 3.1.2,ANNEX 3.1.3,ANNEX 3.1.4,ANNEX 3.1.5)
2 | Publication of annual financial statement on website | Sept 2016 | Annual Financial Statements and budget of municipalities till 2017-18 | ANNEX 3.2
3 | Appointment of internal auditor | March 2017 | The auditor is appointed by ULBs itself here is no appointment of internal auditor | ANNEX 3.3
4 - Urban planning and City Development Plans |  |  |  | 
1 | Preparation of SLIP and SAAP | Mar 2017 | Slip for water supply completed Slip for park completed | ANNEX 4.1
2 | Develop at least one children park every year in the AMRUT cities | Mar 2017 (REPEAT) | Ongoing Tender( Technical Bid) has been open for (Bhagat singh park is selected for SAAP Year-2015-16 & pandit deendayal upadhayay park is selected for SAAP Year 2016-2017 and Cancellation of jessij park tender(dated from27-02-2018 to 26-03-2018) is selected for SAAP Year-2016-2017 due to after taking the decesion by administration on board meeting’s proposal | ANNEX 4.2
Uttar Pradesh- Reform Milestones under AMRUT

## Slide 5
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
4 - Urban planning and City Development Plans (Contd…) |  |  |  | 
3 | Make action plans to progressively increase green cover in cities to 15% in 5 years. | March 2016 | There is no action Plan of Green cover in NPPJANUPUR | ANNEX 4.3
4 | Energy Efficiency Projects | June 2017 | In energy efficient projects JNPP is implementing energy efficient water pumps & streetlights by EESL..board proposal and audit report submitted by EESL I is attached | ANNEX 4.4
5 | Establish a system for maintaining of parks, playground and recreational areas relying on public private partnerships (PPP) model | Sep 2016 | STATE INITIATIVE | ANNEX 4.5
6 | Make a State Level policy for implementing the parameters given in the National Mission for sustainable habitat | Mar 2017 | STATE INITIATIVE | ANNEX 4.6
7 | Establish Urban Development Authorities | Mar 2018 | STATE INITIATIVE | ANNEX 4.7
8 | Preparation of Master Plan using GIS. | Mar 2019 | STATE INITIATIVE | ANNEX 4.8
Uttar Pradesh- Reform Milestones under AMRUT

## Slide 6
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
5 - Devolution of funds and functions |  |  |  | 
1 | Ensure transfer of 14th FC devolution to ULBs | Sept 2016 | The 14 th FC fund transferred electronically to ULBs bank account directly within stipulated time completed | ANNEX 5.1
2 | Appointment of State Finance Commission (SFC) and making decisions | Sept 2016 | STATE INITIATIVE | ANNEX 5.2
3 | Transfer of all function to ULBs | Sept 2016 | STATE INITIATIVE | ANNEX 5.3
4 | Implementation of SFC recommendations within timeline | March 2017 | STATE INITIATIVE | ANNEX 5.4
6 – Revision of Building Bye-Laws |  |  |  | 
1 | Revision of Building bye laws periodically | Sept 2016 | States has adopted ten point model building bye-laws 2016 implemented by VINIYAMIT CHHETRA Jaunpur | ANNEX 6.1
2 | Create single window clearance for all approvals to give building permissions | Sept 2016 | States has adopted ten point model building bye-laws 2016 implemented by VINIYAMIT CHHETRA Jaunpur | ANNEX 6.2
3 | Adoption of Model Building Bye-Laws-2016 | Mar 2017 | States has adopted ten point model building bye-laws 2016 implemented by VINIYAMIT CHHETRA Jaunpur | ANNEX 6.3
Uttar Pradesh- Reform Milestones under AMRUT

## Slide 7
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
7 – Set-up financial intermediary at state level |  |  |  | 
1 | Establish and operationalize financial intermediary- pool finance, access external funds, float municipal bonds | March 2017 | STATE INITIATIVE | ANNEX 7.1
8a- Municipal tax and fees improvement |  |  |  | 
1 | At least 90% Coverage & At least 90% Collection | Sep 2016 | At present 96.95% coverage & 99.94% collection completed | ANNEX 8a.1.1 & ANNEX 8a.1.2
2 | Make policy to periodically revise property tax, levy charges and other fees | Sep 2016 | According to bye lows self assessment is implemented from 2015 & all collection is done according to assessment . | ANNEX 8a.2
3 | Post demand collection book (DCB) of tax details on the website | Sep 2016 | Demand collection Book (DCB) of Tax details has been posted on web site and same is enclosed as Annex 8a.3 | ANNEX 8a.3
4 | Achieve full potential advertisement revenue by making a policy for destination specific potential having dynamic pricing module. | Sep 2016 | Advertisement bye laws dated 1st april 2015 has been implemented in Nagar Palika Parishad Jaunpur. Currently advertisement is being done on contract basis. | ANNEX 8a.4
Uttar Pradesh- Reform Milestones under AMRUT

## Slide 8
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
8b- Improvement in levy and collection of user charges |  |  |  | 
1 | Adopt a policy on user charges for individual and institutional assessment in which a differential rate is charged for water use and adequate safeguards are included to take care of interests of the vulnerable. | Sep 2016 | Presently there is no such policy has been adopted. Only fixed water charge is being collected by JAUNPUR NPP from all type of building uses. In future Tax Department will decide differential rate for the use of water for individual and institutional. | ANNEX 8b.1
2 | Make action plan to reduce water losses to less than 20 % and publish on website | Sep 2016 | Water leakage points are being repaired on daily basis due to which water leakage has reduced significantly. And the re-organization of water supply scheme is on progress by Jal Nigam. Illegal water supply are being legalized. Jaunpur nagar palika start 20 % NRW plan on nppjaunpuronline.org | ANNEX 8b.2
3 | Separate accounts for user charges | Sep 2016 | Separate accounts for user charges details attached in ANNEX 8b.3 | ANNEX 8b.3
4 | At least 90 % billing & At least 90% collection | Sep 2016 | At present 100% billing & 80.16% collection for user charges completed | ANNEX 8b.4.1 & ANNEX 8b.4.2
9 – Credit Rating |  |  |  | 
1 | Complete the credit ratings of the ULBs | June 2017 | Credit Rating has been Completed by the awarded agency ‘’IND-BB’’.Credit rating certificate is enclosed as Annex 9.1 | ANNEX 9.1
Uttar Pradesh- Reform Milestones under AMRUT

## Slide 9
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
10 – Energy and water audit |  |  |  | 
1 | Energy (street lights ) and water audit (including non-revenue water or losses audit) | Sept 2016 | Work is under process and audit of energy (streetlights) and water audit(including non-revenue water or losses audit) will be done be EESL | ANNEX 10.1
2 | Making STPs and WTPs energy efficient | Sept 2016 | Old WTPs is running but STPs is not available in jaunpur required information has been sent to the EESL. | ANNEX 10.2
3 | Optimize energy consumption in street lights by using energy efficient lights and increasing reliance on renewable energy | Sept 2016 | Already given to requirement data regarding street light to the EESL and sending the proposal from EESL to NPP Jaunpur. Total 1040 light point convert in LED light in JNNP. | ANNEX 10.3
4 | Waste Water recycling | March 2017 | STATE INITIATIVE | ANNEX 10.4
5 | Faecal Sludge Management |  | STATE INITIATIVE | ANNEX 10.5
Uttar Pradesh- Reform Milestones under AMRUT

## Slide 10
 | REFORMS | TIMELINE | CURRENT STATUS | ANNEXURE
11 – Swachh Bharat Mission |  |  |  | 
1 | Elimination of open defecation. State sanitation policy notified/city sanitation plans prepared? 2.Percentage of certitified ODF ULB | March 2018 | city sanitation plans not prepared under process 61.54% ODF in NPP Jaunpur(24 Wards are O.D.F. out of 39 wards) | ANNEX 11.1.1 ANNEX 11.1.2
2 | Waste Collection (100%), 1.Percentage of wards with 100% door to door waste collection 2.Percentage of complaints resolution on swachhta app by ULB 3.Percentage of wards practing 100% source segregation | March 2018 | 48.72% wards with 100% Door To Door waste Collection in 19 wards in NPP Jaunpur maximum complaints resolve by ULB but due to technical issue % of complaint resolution on the screen of swachhta app by ULB showing wrong way. snapshot attached 10.25% wards practing 100% source segregation | ANNEX 11.2.1 ANNEX 11.2.2 ANNEX 11.2.3
3 | Transportation of Waste (100%). 1.Percentage of collected waste being tranported for scientific disposal(scientific landfill or processing) | March 2018 | Scientific landfill Under construction | ANNEX 11.3
4 | Scientific Disposal (100%). 1.Percentage of waste being processed scientifically | March 2018 | N/A | ANNEX 11.4
Uttar Pradesh- Reform Milestones under AMRUT